## Start here
Wedding Planner Workbook
Fill in the tinted cells. Every other sheet works from them.
Inside
| Your names | Ava & Tom | Dashboard | Days to go, money, RSVPs, tasks and suppliers at a glance
| Wedding date | 2027-03-20 | Checklist | About 70 tasks from 12 months out to the thank-you notes, dated from your wedding day
| Ceremony time | 15:30 | Budget | Estimate, quote, actual and paid for every line, with a starting split
| Venue | The Riverbank Room | Payments | Every deposit and balance, with what's due in the next 30 days
| Total budget | 40000 | Guest list | RSVPs, plus-ones, children, dietary needs, tables and gifts
| Number of guests | 120 | RSVPs & meals | Headcount by side, dietary tally and meal choices for the caterer
| Honeymoon starts |  | Seating | Tables, seats and who's left to place
|  |  | Suppliers | Who you're talking to, quotes, deposits and contracts
| Days to go |  | Supplier questions | What to ask before you book, for eleven kinds of supplier
|  |  | Events | Every part of the celebration: the rehearsal dinner to the farewell brunch
| How to use it |  | Wedding day | The run sheet from getting ready to the last song, timed from your ceremony
| 1. Fill in the tinted cells on this sheet. |  | Supplier briefs | A one-page brief for each supplier, written from your details
| 2. Work down the Checklist — the dates move with your wedding date. |  | Wedding party | Who's who, their outfits and their jobs on the day
| 3. Keep the Budget and Payments up to date as quotes come in. |  | Attire & beauty | Outfits, fittings, rings, hair and makeup
| 4. Share a copy with your planner or wedding party when it helps. |  | Styling | Every piece of décor, who brings it and who packs it down
|  |  | Stationery | Save the date to thank-you cards: quantities and order dates
| A filled-in example for an invented couple, so you can see every sheet at work. Your own copy starts from your names, date and budget. |  | Gifts & thank-yous | Who gave what, and whether you've said thank you
|  |  | Honeymoon | Budget, bookings, a day-by-day plan and the packing list
|  |  | Contacts & notes | Every number you'll need on the day, and room for notes

## Dashboard
Dashboard
Updates by itself as you fill in the other sheets.
| DAYS TO GO |  | BUDGET BOOKED |  | RSVPS IN |  | CHECKLIST DONE
| Up next |  |  |  | Payments coming up
| Due | Task |  |  | Due | Who and what |  | Amount
| Still to book |  |  |  | Who's coming
| Supplier | Where it's at | [5 empty] | People
Said yes
Said no
Still to reply
People coming, plus-ones included
Still to seat
Thank-you cards to send
Where the money goes
| Category | Planned | Booked | Paid | Share
Venues & stays
Food & drink
Photo, video & content
Music & entertainment
Flowers & styling
Attire & beauty
Stationery

## Checklist
Checklist
Dated from your wedding day. Overdue tasks turn red; the next 30 days are tinted.
|  |  | Done |  | Overdue
When | Task | Area | Due | Status | Who | Notes
12 months or more | Agree the total budget and who is contributing | Money | 2026-02-13 | Done | Ava
12 months or more | Pick a season and two or three possible dates | Planning | 2026-02-18 | Done | Tom
12 months or more | Draft the first guest list and a rough number | Guests | 2026-02-23 | Done | Ava
12 months or more | Decide the feel: size, style, city or away | Planning | 2026-02-28 | Done | Tom
12 months or more | Visit venues and book the ceremony and reception | Venue | 2026-03-05 | Done | Ava
12 months or more | Book your celebrant or officiant | Ceremony | 2026-03-10 | Done | Tom
12 months or more | Decide whether you want a planner or a day coordinator | Planning | 2026-03-15 | Done | Ava
12 months or more | Check the legal paperwork and deadlines where you're marrying | Ceremony | 2026-03-20 | Done | Tom
10 to 12 months | Look into wedding insurance | Money | 2026-03-25 | Done | Ava
10 to 12 months | Book the photographer | Suppliers | 2026-04-14 | Done | Tom
10 to 12 months | Book the videographer | Suppliers | 2026-04-19 | Done | Ava
10 to 12 months | Book the band or DJ | Suppliers | 2026-04-24 | Done | Tom
10 to 12 months | Book the caterer, if the venue doesn't cater | Suppliers | 2026-04-29 | Done | Ava
10 to 12 months | Ask your wedding party | People | 2026-05-04 | Done | Tom
10 to 12 months | Start your wedding website | Guests | 2026-05-09 | Done | Ava
10 to 12 months | Send save the dates (earlier if guests must travel) | Guests | 2026-05-14 | Done | Tom
10 to 12 months | Start looking for outfits | Attire | 2026-05-19 | Done | Ava
8 to 10 months | Order the wedding outfits | Attire | 2026-06-13 | Done | Tom
8 to 10 months | Book the florist and stylist | Suppliers | 2026-06-23 | Done | Ava
8 to 10 months | Book hair and makeup, with a trial date | Attire | 2026-06-28 | Done | Tom
8 to 10 months | Hold a block of rooms for guests who stay over | Guests | 2026-07-03 | Done | Ava
8 to 10 months | Start planning the honeymoon and check passports | Honeymoon | 2026-07-08 | Done | Tom
8 to 10 months | Book transport for the day | Suppliers | 2026-07-13 | Done | Ava
6 to 8 months | Choose the stationery | Stationery | 2026-08-12 | Done | Tom
6 to 8 months | Book the cake maker and arrange a tasting | Suppliers | 2026-08-17 | Done | Ava
6 to 8 months | Book the menu tasting | Food | 2026-08-22 | Done | Tom
6 to 8 months | Book hire items: furniture, marquee, lighting | Styling | 2026-09-01 | Done | Ava
6 to 8 months | Set up the gift list or wishing well | Gifts | 2026-09-06 | Done | Tom
6 to 8 months | Book the rehearsal dinner, if you're having one | Planning | 2026-09-11 | Doing | Ava
4 to 6 months | Go through the ceremony with your celebrant | Ceremony |  | To do
4 to 6 months | Buy the rings | Attire |  | To do
4 to 6 months | Draft the wedding-day timeline | Planning |  | To do
4 to 6 months | Book the honeymoon | Honeymoon |  | To do
4 to 6 months | Choose the wedding party's outfits | Attire |  | To do
2 to 3 months | Send the invitations | Guests |  | To do
2 to 3 months | Write your vows | Ceremony |  | To do
2 to 3 months | Choose the music: aisle, signing, first dance, last song | Ceremony |  | To do
2 to 3 months | Confirm the menu and drinks | Food |  | To do
2 to 3 months | First outfit fitting | Attire |  | To do
2 to 3 months | Order favours and gifts for the wedding party | Gifts |  | To do
2 to 3 months | Buy shoes and accessories | Attire |  | To do
1 month | Chase the RSVPs you're still waiting on | Guests |  | To do
1 month | Give final numbers and dietary needs to the venue and caterer | Food |  | To do
1 month | Make the seating plan | Guests |  | To do
1 month | Confirm every supplier and send them the timeline | Suppliers |  | To do
1 month | Lodge the legal paperwork by the deadline where you're marrying | Ceremony |  | To do
1 month | Final fitting, and wear your shoes in | Attire |  | To do
1 month | Print menus, place cards and signs | Stationery |  | To do
1 month | Write the speeches | People |  | To do
2 weeks | Pay the final balances that are due | Money |  | To do
2 weeks | Confirm final numbers with the caterer | From your plan | 2027-03-06 | To do | Tom
2 weeks | Send the run sheet to the wedding party | People |  | To do
2 weeks | Confirm transport pick-up times and addresses | Suppliers |  | To do
2 weeks | Collect the outfits | Attire |  | To do
2 weeks | Pack for the honeymoon | Honeymoon |  | To do
The week of | Drop styling items and signs at the venue | Styling |  | To do
The week of | Put supplier payments and tips in labelled envelopes | Money |  | To do
The week of | Pack an emergency kit: needle, thread, plasters, pain relief, snacks | Planning |  | To do
The week of | Hand the rings and the run sheet to someone you trust | People |  | To do
The week of | Rehearse the ceremony | Ceremony |  | To do
The day before | Rehearsal dinner, or a quiet dinner together | Planning |  | To do
The day before | Lay out everything you need for the morning | Planning |  | To do
The day before | Charge phones and get an early night | Planning |  | To do
On the day | Eat a proper breakfast | Planning |  | To do
On the day | Hand your phone to someone and enjoy the day | Planning |  | To do
After the wedding | Return hire items and collect your things from the venue | Styling |  | To do
After the wedding | Finish your album and film from everyone's moments | Keepsakes |  | To do
After the wedding | Have the outfit cleaned and the flowers preserved | Attire |  | To do
After the wedding | Review your suppliers | Suppliers |  | To do
After the wedding | Send the thank-you notes | Gifts |  | To do
After the wedding | Update your name on documents, if you're changing it | Ceremony |  | To do

## Budget
Budget
Start from the split, then put in quotes and actual costs. Still to pay works itself out.
|  | Estimate |  | Actual |  | Still to pay |  | Paid
Category | Item | Supplier | Estimate | Quoted | Actual | Paid | Still to pay | Due | Notes
Venues & stays | Reception venue | The Riverbank Room | 12000 | 11500 | 11500 | 3000 |  | 2027-01-15
Venues & stays | Ceremony garden | The Riverbank Room | 1500 | 1200 |  | 1200
Food & drink | Catering, 120 guests | Harvest Table Catering | 9000 | 9600 |  | 2000 |  | 2027-02-20
Food & drink | Wedding cake | Sugar & Fern | 900 | 850
Photo, video & content | Photography, full day | Northlight Photography | 4500 | 4200 |  | 1000 |  | 2027-03-01
Music & entertainment | Band, reception | The Late Arrivals | 3200 | 3400 |  | 500
Flowers & styling | Florals and arbour | Wild Bloom Studio | 3000 | 2750 |  | 750
Attire & beauty | Wedding dress |  | 2500 |  | 2300 | 2300
Stationery | Invitations and signage |  | 600 | 540 |  | 540

## Payments
Payments
Every deposit and balance. Overdue turns red; the next 30 days are tinted.
| Still to pay |  | Due in 30 days
Supplier | For | Amount | Due | Paid on | How | Status | Notes
The Riverbank Room | Reception venue | 8500 | 2027-01-15 |  |  | To pay | From your budget
Harvest Table Catering | Catering, 120 guests | 7600 | 2027-02-20 |  |  | To pay | From your budget
Northlight Photography | Photography, full day | 3200 | 2027-03-01 |  |  | To pay | From your budget

## Guest list
Guest list
One row per invitation. Headcount counts the guest, their plus-ones and children once they say yes.
Invited |  | Coming |  |  | Waiting
Name | Side | Household | Email | Mobile | Address | Invited to | Save the date sent | Invitation sent | RSVP | Plus-ones | Children | Headcount | Dietary | Access needs | Meal | Table | Gift | Thank-you sent | Notes
Grace Miller | Ava's | Miller |  |  |  | Family |  |  | Yes | 1 |  |  |  |  | Fish | Table 1 | Honeymoon fund | Yes
Peter Miller | Ava's | Miller |  |  |  | Family |  |  | Yes | [5 empty] | Beef | Table 1
Hannah Brooks | Ava's |  |  |  |  | Friends |  |  | Yes |  |  |  | Vegetarian |  | Vegetarian | Table 2
Oliver Grant | Tom's |  |  |  |  | Family |  |  | Yes | 1 |  |  |  |  | Beef | Table 3
Chloe Grant | Tom's |  |  |  |  | Family |  |  | Yes |  |  |  | No shellfish |  | Fish | Table 3
Marcus Lee | Tom's |  |  |  |  | Friends |  |  | Waiting |  | 2
Sofia Diaz | Both |  |  |  |  | Friends |  |  | No
Liam O'Connor | Tom's |  |  |  |  | Friends |  |  | Yes | [5 empty] | Beef | Table 4
Emily Carter | Ava's |  |  |  |  | Friends |  |  | Yes |  |  |  | Vegan |  | Vegetarian | Table 2
Jack Thompson | Tom's |  |  |  |  | Work |  |  | Yes | [5 empty] | Fish | Table 4
Isla Robertson | Ava's |  |  |  |  | Work |  |  | Waiting | 1
Noah Walker | Both |  |  |  |  | Friends |  |  | Yes |  |  |  |  | Step-free access | Beef | Table 5
Ruby Hughes | Ava's |  |  |  |  | Family |  |  | Yes |  |  |  | Gluten free |  | Fish | Table 1
Henry Clarke | Tom's |  |  |  |  | Work |  |  | No
Zoe Mitchell | Both |  |  |  |  | Friends |  |  | Yes | 1 |  |  |  |  | Vegetarian | Table 5
Ethan Wright | Tom's |  |  |  |  | Family |  |  | Yes | [5 empty] | Beef | Table 3 | Champagne flutes
Mia Bennett | Ava's |  |  |  |  | Friends |  |  | Waiting
Lucas Fraser | Tom's |  |  |  |  | Friends |  |  | Yes | [5 empty] | Fish | Table 4
Amelia Scott | Ava's |  |  |  |  | Family |  |  | Yes |  | 1 |  |  |  | Beef | Table 2
James Porter | Both |  |  |  |  | Friends |  |  | Yes | [5 empty] | Vegetarian | Table 5

## RSVPs & meals
RSVPs & meals
For the caterer: numbers, dietary needs and meal choices from the guest list.
Who's coming |  |  | The menu
| Invitations | People | Course | What we're serving
Invited |  |  | Canapés
Yes |  |  | Entrée
No |  |  | Main
Waiting |  |  | Dessert
Children coming |  |  | Cake
Late-night snack
By side
Side | Invitations | Coming | Drinks
Ava's |  |  | Drink | Supplier, package and cost
Tom's |  |  | Welcome drink
Both |  |  | Beer and cider
Neither |  |  | Wine
Spirits
Dietary needs (guests who said yes) |  |  | Non-alcoholic
Need | Guests |  | The toast
Vegetarian
Vegan
Gluten free
Dairy free
Nut allergy
Seafood allergy
Halal
Kosher
Meal choices
Option (as written in the Meal column) | Chosen
Fish
Beef
Vegetarian

## Seating
Seating
Seated counts everyone on the guest list at that table who's coming, plus-ones included.
Coming |  | Seated |  | Still to place
Table | For | Shape | Seats | Seated | Free | Notes
Table 1 | Reception | Round | 10
Table 2 | Reception | Round | 10
Table 3 | Reception | Round | 10
Table 4 | Reception | Round | 10
Table 5 | Reception | Round | 10

## Suppliers
Suppliers
Everyone you're talking to. Compare them with the questions on the next sheet.
Booked |  | Still deciding
Category | Business | Contact | Phone | Email | Website | Quote | Status | Deposit paid | Balance due | Contract signed | Notes
Venue | The Riverbank Room | Claire | 0400 000 101 | events@example.com |  | 12700 | Booked
Catering | Harvest Table Catering | Sam | 0400 000 102 |  |  | 9600 | Booked
Photo, video & content | Northlight Photography | Daniel | 0400 000 103 |  |  | 4200 | Booked
Music & entertainment | The Late Arrivals | Jess | 0400 000 104 |  |  | 3400 | Quote in
Flowers & styling | Wild Bloom Studio | Nina | 0400 000 105 |  |  | 2750 | Booked
Cake | Sugar & Fern | Holly |  |  |  | 850 | Asked for a quote
MC | Rory Bell, MC | Rory | 0400 000 106 |  |  | 900 | Booked

## Supplier questions
Supplier questions
Ask the same questions of everyone you're comparing, and note the answers side by side.
Venue
Question | Option A | Option B | Option C
Who you're comparing
Is our date free, and how long can you hold it for us?
What does the hire fee include: tables, chairs, linen, staff, set-up?
How many guests fit seated, and how many standing?
What's the plan if it rains?
When can suppliers arrive, and when must everything be out?
Is there a noise limit or a finish time?
Can we bring our own caterer, drinks or suppliers?
What's the deposit, the payment schedule and the cancellation policy?
Photographer
Question | Option A | Option B | Option C
Who you're comparing
Can we see two complete weddings you've shot, not just the highlights?
Who will photograph our day, and is there a second shooter?
How many hours are included, and what does extra time cost?
When will we get the photos, and roughly how many?
Do we get the full-size files and the right to print them?
What happens if you're ill or your gear fails?
Videographer
Question | Option A | Option B | Option C
Who you're comparing
Can we watch a full ceremony film, not only a highlights reel?
Do you record the vows and speeches with separate microphones?
What do we get: a highlight film, the full ceremony, raw footage?
How long until the films are ready?
Will you work alongside our photographer without getting in shots?
Do you use a drone, and is it allowed at our venue?
Caterer
Question | Option A | Option B | Option C
Who you're comparing
What's the price per head, and what's included?
Can we do a tasting before we confirm the menu?
How do you handle allergies and dietary needs?
Do you supply staff, plates, glasses and linen?
Is a drinks package available, and how is it charged?
When do you need final numbers?
Florist & stylist
Question | Option A | Option B | Option C
Who you're comparing
What flowers will be in season for our date?
Can you work to our budget and show us a mock-up?
Do you deliver, set up and pack down?
Can ceremony flowers be moved to the reception?
Which items are hired, and which do we keep?
What's the deposit, and when is the balance due?
Celebrant
Question | Option A | Option B | Option C
Who you're comparing
Can you take us through the legal steps and the deadlines where we're marrying?
How many times will we meet, and do you write the ceremony with us?
Is a rehearsal included?
Do you bring a microphone and speaker?
Can family or friends do readings or a ritual?
What does it cost, and what if the date changes?
Band or DJ
Question | Option A | Option B | Option C
Who you're comparing
Can we hear you live, or see a video of a recent wedding?
Will you play our requests and avoid our do-not-play list?
Do you MC, and announce the entrances and speeches?
What equipment do you bring, and what do you need from the venue?
How long do you play, and how are breaks covered?
What do you need from us beforehand?
Hair & makeup
Question | Option A | Option B | Option C
Who you're comparing
Is a trial included, and when should we book it?
How many people can you do, and how long each?
Do you come to us, and is there a travel fee?
Will you stay for touch-ups?
What products do you use, for sensitive skin too?
What's the deposit and the cancellation policy?
Cake
Question | Option A | Option B | Option C
Who you're comparing
Can we taste flavours before we choose?
How many serves do we need for our numbers?
Do you deliver and set up the cake?
Can you cater for allergies or a dietary need?
Does the venue charge a cake-cutting fee?
When do you need the final design?
Transport
Question | Option A | Option B | Option C
Who you're comparing
Which cars or buses are available on our date?
How many hours are included, and what's the overtime rate?
Is there a backup vehicle if one breaks down?
Will the driver dress for the day and decorate the car?
Can you move guests between the ceremony and the reception?
What's the deposit and the balance date?
Planner or coordinator
Question | Option A | Option B | Option C
Who you're comparing
Do you plan the whole wedding, or coordinate the day only?
How many weddings do you take on at once?
Will you be there all day, and who else is on your team?
Do you have suppliers you recommend, and are you paid by them?
How do you keep us up to date?
How is your fee worked out?

## Events
Events
Every part of the celebration, in order.
Event | Date | Starts | Length (min) | Ends | Venue | Dress code | Notes
Welcome drinks | 2027-03-19 | 18:00 | 150 |  | The Boathouse Bar | Smart casual
Ceremony | 2027-03-20 | 15:30 | 30 |  | The Garden | Cocktail
Reception | 2027-03-20 | 17:30 | 330 |  | The Riverbank Room | Cocktail
Farewell brunch | 2027-03-21 | 10:30 | 120 |  | Ava's parents' home | Relaxed

## Wedding day
Wedding day
Times follow your ceremony time on Start here. Change a row's time by typing over it.
Time | Length (min) | What | Where | Who | Notes
| 180 | Hair and makeup begins | Getting ready | Hair & makeup
| 60 | Photographer arrives for getting-ready photos | Getting ready | Photographer
| 15 | Flowers delivered: bouquets and buttonholes | Getting ready | Florist
| 30 | Get dressed | Getting ready | Couple and wedding party
| 30 | First look and a few portraits (optional) | Getting ready | Photographer
| 30 | Leave for the ceremony | Transport | Driver
| 30 | Guests arrive; music starts | Ceremony | Ushers, musician
| 10 | Wedding party lines up | Ceremony | Celebrant, coordinator
| 30 | Ceremony | Ceremony | Celebrant
| 10 | Confetti and congratulations | Ceremony | Everyone
| 20 | Family group photos | Ceremony | Photographer, a helper with the list
| 60 | Couple portraits; drinks and canapés for guests | Reception | Photographer, caterer
| 15 | Guests take their seats | Reception | MC
| 10 | Grand entrance | Reception | MC, DJ
| 30 | Entrée served | Reception | Caterer
| 30 | Speeches | Reception | MC
| 30 | Main course | Reception | Caterer
| 10 | Cut the cake | Reception | MC, photographer
| 5 | First dance | Reception | DJ or band
| 70 | Dance floor opens | Reception | DJ or band
| 20 | Dessert or a late snack | Reception | Caterer
| 15 | Last song and send-off | Reception | DJ, MC
| 60 | Pack down and collect your things | Reception | Coordinator, suppliers

## Supplier briefs
Supplier briefs
Each supplier's page, written from the rest of this workbook. Print it or paste it into an email.
For the caterer | For the MC
Booked | Booked
Date | The couple
Venue | Guests seated
Guests eating | Grand entrance
Children's meals | Speeches
Dietary needs | Speakers
Meal choices | Cake
Canapés from | First dance
Entrée served | Last song and send-off
Main course | Names to say right
Dessert or late snack | Announcements
Anything else for them
For the band or DJ
For the photographer | Booked
Booked | Guests arrive, music starts
Date | Grand entrance
Getting-ready photos | First dance
First look | Dance floor opens
Ceremony | Last song
Family groups | Aisle song
Couple portraits | First dance song
Venue | Last song
Must-have shots | Never play
Family groups list
For the venue
Booked
Date
Ceremony
Guests coming
Tables
Pack down from
Supplier arrival times
Layout notes

## Wedding party
Wedding party
Who's who, what they wear and what they do on the day.
Role | Name | Phone | Email | Outfit | Jobs on the day | Speech | Notes
Maid or man of honour
Best man or best person
Attendant
Attendant
Attendant
Groomsman or groomswoman
Groomsman or groomswoman
Flower child
Ring bearer
Usher
Usher
MC
Reader
Witness
Witness

## Attire & beauty
Attire & beauty
Outfits, fittings, rings, hair and makeup.
Cost
Item | For | Shop or supplier | Order by | Fittings | Cost | Paid | Status | Notes
Wedding outfit (1) | [6 empty] | To do
Wedding outfit (2) | [6 empty] | To do
Alterations | [6 empty] | To do
Shoes | [6 empty] | To do
Veil, hair piece or tie | [6 empty] | To do
Jewellery and cufflinks | [6 empty] | To do
Underwear and shapewear | [6 empty] | To do
Wedding rings | [6 empty] | To do
Hair trial | [6 empty] | To do
Makeup trial | [6 empty] | To do
Wedding party outfits | [6 empty] | To do
Going-away outfit | [6 empty] | To do

## Styling
Styling
Every piece of décor, who brings it, and who packs it down.
Cost
Item | Area | Qty | Supplier or DIY | Cost | Status | Who brings it | Who packs it down | Notes
Ceremony arch or backdrop | Ceremony |  |  |  | Idea
Aisle flowers or markers | Ceremony |  |  |  | Idea
Ceremony seating | Ceremony |  |  |  | Idea
Signing table and chairs | Ceremony |  |  |  | Idea
Welcome sign | Entrance |  |  |  | Idea
Seating chart | Entrance |  |  |  | Idea
Guest book | Entrance |  |  |  | Idea
Card or gift box | Entrance |  |  |  | Idea
Centrepieces | Reception |  |  |  | Idea
Table linen and napkins | Reception |  |  |  | Idea
Candles and lighting | Reception |  |  |  | Idea
Head table styling | Reception |  |  |  | Idea
Cake table | Reception |  |  |  | Idea
Photo backdrop | Reception |  |  |  | Idea

## Stationery
Stationery
Quantities start from your guest list. Order and send dates follow your wedding date.
Item | Qty | Supplier | Order by | Send by | Cost | Status | Notes
Save the date | [5 empty] | To do
Invitation | [5 empty] | To do
Details card (stay, travel, dress code) | [5 empty] | To do
Ceremony programme | [5 empty] | To do
Menu | [5 empty] | To do
Place cards | [5 empty] | To do
Table numbers | [5 empty] | To do
Seating chart | [5 empty] | To do
Signs | [5 empty] | To do
Thank-you cards | [5 empty] | To do
Save the date: three ways to say it
Save the date! [Name] and [Name] are getting married on [date] in [place]. Invitation to follow.
We said yes. Keep [date] free for our wedding in [place] — the details are on their way.
Pack a bag for [date]: we're getting married in [place], and we'd love you there. More soon.
Make the save the date and invitation in Capsemble (Studio → Invitations): guests reply online, and their answers fill your guest list.

## Gifts & thank-yous
Gifts & thank-yous
Who gave what, and whether you've said thank you.
Gifts |  | Thank-yous to send
From | Gift | Received | Value | Thank-you sent | Sent on | Notes
Grace Miller | Contribution to the honeymoon fund |  | 150 | Yes
Ethan Wright | Champagne flutes |  |  | No

## Honeymoon
Honeymoon
Set the start date on Start here and the day-by-day plan dates itself.
Budget
Item | Estimate | Actual | Paid
Flights
Accommodation
Transfers and car hire
Activities and tours
Food and drink
Travel insurance
Spending money
Other
Total
Bookings
Booking | Provider | Confirmation | From | To | Cost | Paid | Status
Flight out | [6 empty] | Looking
Flight home | [6 empty] | Looking
Accommodation (1) | [6 empty] | Looking
Accommodation (2) | [6 empty] | Looking
Airport transfer | [6 empty] | Looking
Car hire | [6 empty] | Looking
Tour or activity | [6 empty] | Looking
Restaurant | [6 empty] | Looking
Day by day
Day | Date | Where | Staying at | Plan
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Day 8
Day 9
Day 10
Day 11
Day 12
Day 13
Day 14
Packing
Item | Packed
Passports, with the expiry dates checked
Visas or travel permits, if needed
Travel insurance documents
Booking confirmations
Cards and some local cash
Phone chargers and an adaptor
Medicines and prescriptions
Sunscreen and swimwear
Something to dress up in
Comfortable shoes

## Contacts & notes
Contacts & notes
Every number you'll need on the day. Print it for whoever is running the day.
Who | Name | Business | Phone | Email | Arrives at | Notes
Venue coordinator
Celebrant
Planner or coordinator
Photographer
Videographer
Caterer
Florist or stylist
Band or DJ
Hair & makeup
Transport
Cake
Accommodation
Emergency contact on the day
Venue | Claire | The Riverbank Room | 0400 000 101 | events@example.com
Catering | Sam | Harvest Table Catering | 0400 000 102
Photo, video & content | Daniel | Northlight Photography | 0400 000 103
Music & entertainment | Jess | The Late Arrivals | 0400 000 104
Flowers & styling | Nina | Wild Bloom Studio | 0400 000 105
Cake | Holly | Sugar & Fern
MC | Rory | Rory Bell, MC | 0400 000 106
Notes